## Effort Estimation
No | Functionality Type | Module | Features | Complexity (Tech Lead) | Interface Type | HTML (hrs) | ReactJS (hrs) | Python (hrs) | AI (hrs) | DevOps (hrs) | Remarks - Tech Team | BA Remarks (fill manually)
A.0 | Project Setup | - | Full-stack project initialization. Sub-tasks: (1) Monorepo setup with frontend/backend separation, (2) Docker compose for local development, (3) Azure DevOps CI/CD pipeline configuration, (4) Azure environment provisioning with resource groups and key vaults | Medium-High | Web + Backend + AI + Cloud | 0 | 0 | 0 | 0 | 40 | Critical path — all other modules depend on this. CI/CD and environment setup must be done first.
B.0 | Identity & Access | Auth & RBAC | Implement login, JWT issuance, role-based permissions. Sub-tasks: (1) UI login screens with validation, (2) Azure AD SSO integration and token handling, (3) Backend APIs for authentication and role checks, (4) RBAC claims mapping in JWT, (5) Unit tests for auth flows | High | Web + Backend | 8 | 12 | 20 | 0 | 4 | Uses Azure AD groups; assumes JWT stateless auth—no session store needed.
B.1 | Identity & Access | SSO Integration | Configure Azure Entra ID single sign-on for all users. Sub-tasks: (1) Register application in Azure AD, (2) Configure redirect URIs and scopes, (3) Implement token validation middleware | Medium | Web | 4 | 8 | 12 | 0 | 2 | Assumes Entra ID tenant already exists; no extra licensing required.
C.0 | Candidate Management | Candidate Portal UI | Design responsive candidate-facing portal. Sub-tasks: (1) Landing page with branding, (2) Dashboard showing application status, (3) Navigation to profile, interview schedule, document upload, (4) Accessibility compliance checks | Medium-High | Web | 12 | 24 | 0 | 0 | 0 | Critical for candidate adoption; uses Azure Static Web Apps hosting.
C.1 | Candidate Management | Candidate Upload API | Expose REST endpoint for resume upload. Sub-tasks: (1) API contract definition, (2) Validation and size limits, (3) Store file in Azure Blob Storage and emit Service Bus message | Medium | API | 0 | 0 | 12 | 0 | 4 | Depends on Blob Storage provisioning (row Q.0).
C.2 | Candidate Management | Resume Parsing Pipeline | Asynchronous resume extraction and indexing. Sub-tasks: (1) Service Bus trigger listener, (2) Call Azure Form Recognizer, (3) Parse JSON to candidate model, (4) Persist to Azure SQL, (5) Index into Cognitive Search | High | Backend + AI | 0 | 0 | 18 | 20 | 4 | Latency risk with Form Recognizer; async design adds buffer.
D.0 | Job Management | Job CRUD UI | Create, edit, retire job postings. Sub-tasks: (1) Job form UI with validation, (2) API endpoints for CRUD operations, (3) Frontend integration with job list component | Medium | Web | 10 | 20 | 0 | 0 | 0 | Depends on backend job service (planned within same sprint).
E.0 | Search | Candidate Search UI | Fast candidate search with filters and scoring. Sub-tasks: (1) Search bar component, (2) Facet filters UI, (3) Integration with Azure Cognitive Search API, (4) Result ranking and pagination logic | Medium-High | Web | 8 | 20 | 8 | 0 | 0 | Requires search index schema (row R.0) and caching strategy.
F.0 | Dashboard | Recruiter Dashboard | Recruiter KPI overview and candidate funnel. Sub-tasks: (1) Widget layout design, (2) API aggregation for metrics, (3) Chart components with Power BI embed, (4) Refresh and drill-down interactions | Medium-High | Web | 10 | 22 | 12 | 0 | 0 | Critical path — recruiter productivity depends on accurate metrics.
F.1 | Dashboard | Hiring Manager Dashboard | Hiring manager view with pipeline status and budget. Sub-tasks: (1) Dashboard layout mirroring recruiter view, (2) API calls for manager-specific data, (3) Interactive charts for time-to-hire, (4) Export to CSV functionality | Medium-High | Web | 10 | 22 | 12 | 0 | 0 | Shares components with recruiter dashboard; reuse reduces risk.
G.0 | Interview Scheduling | Scheduling UI & Outlook Integration | Calendar UI for interview slots and automatic Outlook event creation. Sub-tasks: (1) UI calendar component with availability picker, (2) Backend service to call Outlook Calendar API, (3) Conflict detection logic, (4) Email invitation generation, (5) Sync status updates to candidate portal | High | Web + Integration | 0 | 12 | 20 | 0 | 0 | Depends on Outlook connector (row J.2); latency of calendar API a risk.
H.0 | Notifications | Notification Service | Send email/SMS alerts for status changes. Sub-tasks: (1) Template library for different notification types, (2) Service Bus topic for async dispatch, (3) Integration with SendGrid or Twilio APIs | Medium | Backend | 0 | 0 | 12 | 0 | 4 | Assumes third‑party provider credentials are available.
I.0 | Reporting & Analytics | Power BI Embedded UI | Embed executive dashboards in application. Sub-tasks: (1) Power BI workspace and dataset provisioning, (2) Frontend component for iframe embed with auth, (3) Row-level security implementation, (4) Data refresh scheduling, (5) Export to PDF option | High | Web | 0 | 12 | 20 | 0 | 0 | Relies on Azure Synapse Serverless for data aggregation; licensing assumed.
J.0 | Integration | Workday Connector | Synchronize employee and job data with Workday. Sub-tasks: (1) Logic App workflow design, (2) Data mapping schema definition, (3) Incremental delta extraction, (4) Error handling and retry policies, (5) Manual import fallback UI | High | Integration | 0 | 0 | 24 | 0 | 4 | Risk of missing fields; PoC needed early.
J.1 | Integration | Teams Connector | Post candidate updates and chat links to Microsoft Teams channels. Sub-tasks: (1) Logic App Teams connector, (2) Message formatting template, (3) Mapping of recruiter actions to Teams events, (4) Permissions handling for posting in different teams | Medium-High | Integration | 0 | 0 | 16 | 0 | 0 | Uses managed Logic Apps; minimal custom code.
J.2 | Integration | Outlook Calendar Connector | Create, update, cancel interview events in Outlook. Sub-tasks: (1) OAuth consent flow for calendar scopes, (2) API wrapper for event CRUD, (3) Time zone conversion logic, (4) Conflict detection fallback | Medium | Integration | 0 | 0 | 14 | 0 | 0 | Depends on Azure AD permissions for calendar access.
K.0 | External Access | Interviewers Guest Access | Allow external interviewers limited portal access via Azure AD B2B. Sub-tasks: (1) Guest account provisioning workflow, (2) RBAC role limited to interview scheduling, (3) GDPR‑compliant consent capture | Medium | Web | 0 | 0 | 12 | 0 | 4 | Potential residency concerns; data stored in EU region.
L.0 | Compliance | Audit Logging & Monitoring | Capture immutable logs for all actions and expose monitoring dashboards. Sub-tasks: (1) Integrate SDK with Application Insights, (2) Configure Log Analytics workspace, (3) Define log schema for audit trails, (4) Build alert rules for suspicious activity, (5) Dashboard view for compliance officers | High | Backend + Monitoring | 0 | 0 | 12 | 0 | 20 | Critical for GDPR; log retention policies defined via Azure Policy.
L.1 | Compliance | GDPR Controls Setup | Enforce data residency, encryption, and retention. Sub-tasks: (1) Azure Policy definitions for storage encryption, (2) Purview data catalog tagging, (3) Retention schedule configuration, (4) Data subject request workflow, (5) Automated compliance reporting | High | Backend | 0 | 0 | 8 | 0 | 24 | Assumes Purview subscription is available; adds ~2 weeks config effort.
M.0 | DevOps | CI/CD Pipelines | Automate build, test, and deployment for frontend and backend. Sub-tasks: (1) Azure Pipelines YAML for React app, (2) YAML for .NET API build and containerization, (3) Staging slot deployment with approvals | Medium | DevOps | 0 | 0 | 0 | 0 | 20 | Critical path — ensures rapid delivery of subsequent features.
M.1 | DevOps | Release Management | Manage production releases with blue‑green deployment and rollback. Sub-tasks: (1) Configure Azure Static Web Apps slots, (2) Setup deployment slots for App Service, (3) Define release gates and health checks | Medium | DevOps | 0 | 0 | 0 | 0 | 16 | Ensures 99.9% SLA by enabling quick rollback.
N.0 | Quality Assurance | Testing Suite | Automated unit, integration, and end‑to‑end tests. Sub-tasks: (1) Set up Jest for React components, (2) xUnit for .NET APIs via Python placeholder, (3) Cypress E2E flow covering core user journeys | Medium | Testing | 0 | 0 | 24 | 0 | 0 | Testing framework choices assume existing team expertise.
O.0 | Security | MFA Configuration | Enforce multi‑factor authentication for all users. Sub-tasks: (1) Azure AD MFA policy definition, (2) User onboarding guidance docs, (3) Integration testing of MFA flow | Medium | Backend | 0 | 0 | 6 | 0 | 4 | Assumes Entra ID licensing includes MFA.
O.1 | Security | RBAC Implementation | Map business roles to Azure AD groups and custom JWT claims. Sub-tasks: (1) Define role matrix, (2) Implement claim injection middleware, (3) Unit tests for permission checks | Medium | Backend | 0 | 0 | 12 | 0 | 2 | Technical assumption: Azure AD group sync works without custom sync service.
P.0 | Data Layer | Database Schema Design | Model relational tables for jobs, candidates, applications, and audit. Sub-tasks: (1) ER diagram creation, (2) Entity Framework Core model generation, (3) Migration scripts for initial schema | Medium | Backend | 0 | 0 | 10 | 0 | 2 | Assumes Azure SQL premium tier for performance.
P.1 | Data Layer | Azure SQL Provisioning | Create Azure SQL instance, configure geo‑replication and backups. Sub-tasks: (1) Resource deployment via ARM template, (2) Set up firewall and VNet rules, (3) Configure automated backups and point‑in‑time restore | Medium | DevOps | 0 | 0 | 8 | 0 | 6 | Technical assumption: existing subscription quota suffices.
Q.0 | Caching | Redis Cache Setup | Deploy Azure Cache for Redis and integrate with API for session storage. Sub-tasks: (1) Provision Redis instance, (2) Configure connection strings securely, (3) Implement cache wrapper in backend services | Low | Backend | 0 | 0 | 4 | 0 | 6 | Low risk; basic caching improves latency.
R.0 | Search | Search Index Schema | Define Azure Cognitive Search index fields and scoring profiles. Sub-tasks: (1) Field mapping from candidate model, (2) Synonym map creation, (3) Reindexing script for existing data, (4) Performance testing of query latency | Medium-High | Backend | 0 | 0 | 12 | 0 | 4 | Risk of query slowdown; replica scaling may be needed.
S.0 | AI Services | Resume Parsing Service | Invoke Azure Form Recognizer on uploaded resumes. Sub-tasks: (1) Service Bus trigger to start parsing, (2) Call Form Recognizer with appropriate model, (3) Transform output to candidate entity, (4) Persist results, (5) Fallback keyword parser if AI fails | High | Backend + AI | 0 | 0 | 12 | 20 | 2 | Processing must stay under 10 seconds; async design adds safety buffer.
S.1 | AI Services | Candidate Matching Service | Generate candidate‑role suitability scores using Azure OpenAI. Sub-tasks: (1) Prompt engineering for matching logic, (2) Build API wrapper around Azure OpenAI, (3) Combine AI score with keyword filters, (4) Store score in SQL, (5) Expose score in search results | High | Backend + AI | 0 | 0 | 10 | 24 | 2 | AI must only assist; no automated hiring decisions.
T.0 | Candidate Experience | Candidate Portal Features | Enable status tracking, interview scheduling, document upload, and messaging. Sub-tasks: (1) Status timeline UI, (2) Calendar embed for interview slots, (3) Secure document upload component, (4) In‑portal messaging thread, (5) Notification badge updates | Medium-High | Web | 6 | 16 | 4 | 0 | 0 | Improves candidate satisfaction; depends on scheduling service.
V.0 | Compliance | Audit UI | Web interface for compliance team to query and export audit logs. Sub-tasks: (1) Log query form, (2) Results table with pagination, (3) Export to CSV functionality | Medium | Web | 8 | 12 | 6 | 0 | 0 | Depends on Log Analytics data availability.
W.0 | Performance | Performance Testing & Optimization | Load test critical APIs and tune scaling. Sub-tasks: (1) Script creation for search and parsing endpoints, (2) Execute tests with Azure Load Testing, (3) Analyze latency bottlenecks, (4) Adjust Service Bus and App Service plans | Medium-High | Testing | 0 | 0 | 12 | 0 | 8 | Risk mitigation for <2 s search SLA.
X.0 | Documentation | Documentation & Training Materials | Create developer docs, user guides, and admin training decks. Sub-tasks: (1) Architecture diagram write‑up, (2) API reference markdown, (3) Admin operational guide | Low | Documentation | 4 | 0 | 0 | 0 | 0 | Assumes existing template repository.
Y.0 | Internationalization | Localization Support | Translate UI strings and format dates/currencies for 35 locales. Sub-tasks: (1) Extract i18n keys, (2) Add language files, (3) Implement locale selector, (4) Test date/currency rendering per region | Medium | Web | 6 | 12 | 4 | 0 | 2 | Technical assumption: translation service subscription available.
| TOTALS |  |  |  |  | 86 | 192 | 356 | 64 | 184 | Grand Total: 882 hrs