## Effort Estimation
No | Functionality Type | Module | Feature | Task | Sub Task | Complexity | Dependencies | Backend (hrs) | AI/ML (hrs) | Integration (hrs) | Cloud Infrastructure (hrs) | DevOps (hrs) | Security (hrs) | QA (hrs) | Data Engineering (hrs) | Tech Remarks | BA Remarks
A.1 | Project Setup | - | Repository & CI/CD Init | Initialize mono-repo | Create GitHub repo, set up basic folder structure, add README | Medium |  | 8 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | Foundational repo and CI pipeline; enables downstream automation.
A.2 | Cloud Infrastructure | VPC India | Network Isolation | Create VPC | Define subnets, route tables, NAT gateways for ap-south-1 | Medium | Project Setup | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | Provides isolated networking for all India resources.
A.3 | Cloud Infrastructure | VPC EU | Network Isolation | Create VPC | Define subnets, route tables, NAT gateways for eu-central-1 | Medium | Project Setup | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | Ensures EU data residency and compliance.
A.4 | Cloud Infrastructure | Kubernetes India | EKS Cluster | Provision EKS | Create EKS control plane, node groups, IAM roles for ap-south-1 | High | VPC India | 0 | 0 | 0 | 14 | 6 | 0 | 0 | 0 | Managed K8s foundation for all containerised services.
A.5 | Cloud Infrastructure | Kubernetes EU | EKS Cluster | Provision EKS | Create EKS control plane, node groups, IAM roles for eu-central-1 | High | VPC EU | 0 | 0 | 0 | 14 | 6 | 0 | 0 | 0 | Provides isolated EU compute environment for London desk.
A.6 | Security | IAM & MFA | Identity Management | Configure IAM & SSO | Create IAM roles, enable AWS SSO with MFA, define password policies | Medium | Project Setup | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | Meets SEBI/FCA MFA requirement for all users.
A.7 | Security | RBAC & OPA | Policy Enforcement | Deploy OPA Gatekeeper | Create policies for namespace isolation, enforce least‑privilege access | Medium | IAM & MFA | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | Prevents shared credentials; provides audit‑ready RBAC.
A.8 | Data Engineering | Streaming | Kafka Cluster | Provision MSK | Create Amazon MSK cluster, configure 3‑zone replication, enable encryption at rest | Medium | VPC India, VPC EU | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 12 | Core streaming backbone for market data and signals.
A.9 | Data Engineering | Schema | Protobuf Registry | Deploy Schema Registry | Install Confluent Schema Registry, register canonical tick schema, enforce versioning | Low | Kafka Cluster | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Ensures type‑safe data across all services.
A.10 | Data Engineering | Connectors | Bloomberg Feed | Implement Kafka connector | Build Rust connector consuming Bloomberg API, publish raw ticks to Kafka | Medium-High | Schema Registry | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 12 | Handles Bloomberg licensing constraints; keeps feed within India VPC.
A.11 | Data Engineering | Connectors | Refinitiv Feed | Implement Kafka connector | Build Rust connector for Refinitiv, optional based on client decision | Medium | Schema Registry | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 10 | Can be disabled if client drops Refinitiv.
A.12 | Data Engineering | Connectors | Local NSE Feed | Implement Kafka connector | Build Rust connector for cheap local NSE tick feed, publish to Kafka | Medium-High | Schema Registry | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 12 | Ensures ultra‑low latency for India desk.
A.13 | Backend | Normalization | Tick Normalizer | Develop Rust service | Consume raw Kafka topics, convert to Protobuf, write to QuestDB & Redis | High | Bloomberg Feed, Refinitiv Feed, Local NSE Feed | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Core data pipeline; guarantees schema conformity and low‑latency writes.
A.14 | Backend | Time‑Series Store | QuestDB Deployment | Provision QuestDB | Launch EC2 instances, configure HA autoscaling group, enable secure access | Medium-High | Normalization Service | 16 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | Provides sub‑millisecond reads for model inputs and backtesting.
A.15 | Backend | Cache Layer | Redis Enterprise | Deploy Redis | Create multi‑AZ Redis Enterprise cluster with deterministic latency tier | Medium | Normalization Service | 12 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | Hot cache for execution engine, guarantees tail‑latency <1 ms.
B.1 | AI/ML | MLOps | MLflow Tracking | Deploy MLflow Server | Run MLflow on EKS, configure S3 artifact store and PostgreSQL metadata DB | Medium | Kubernetes Clusters | 0 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | Centralizes experiment tracking and model versioning.
B.2 | AI/ML | Research Env | JupyterHub | Install JupyterHub | Deploy helm chart on EKS, configure python kernels, integrate with QuestDB access | Medium | Kubernetes Clusters, QuestDB | 0 | 14 | 0 | 0 | 6 | 0 | 0 | 0 | Provides analysts with a modern Python research platform.
B.3 | AI/ML | Data Access | Python QuestDB Client | Develop library | Wrap QuestDB SQL via psycopg2/polars, expose convenient data frames for backtesting | Low | QuestDB | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | Standardizes data retrieval for researchers and training pipelines.
B.4 | AI/ML | Model Training | LSTM Signal Generator | Write training script | Implement PyTorch LSTM, hyper‑parameter sweep, log to MLflow | Medium-High | Python QuestDB Client, MLflow | 6 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | First ML model for trend‑following signals.
B.5 | AI/ML | Model Training | Transformer Signal Generator | Write training script | Implement PyTorch Transformer, integrate with MLflow, evaluate on validation set | High | Python QuestDB Client, MLflow | 6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | Provides more expressive temporal modeling for complex strategies.
B.6 | AI/ML | Export | ONNX Conversion | Create export pipeline | Convert trained PyTorch models to ONNX, validate inference parity, store artifacts in S3 | Medium | Model Training | 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | Standardizes model format for low‑latency serving.
B.7 | AI/ML | Model Serving | ONNX Runtime Service | Deploy gRPC service | Containerize ONNX Runtime, expose inference endpoint, auto‑scale based on signal volume | Medium-High | ONNX Conversion, Kubernetes Clusters | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | Delivers <1 ms inference for real‑time signal generation.
B.8 | AI/ML | Shadow Trading | Shadow Mode Framework | Implement orchestration | Route model signals to a parallel execution path, capture performance metrics, enforce 30‑day minimum | Medium | Model Serving | 6 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | Enables safe production rollout of new models.
B.9 | AI/ML | A/B Testing | Challenger vs Champion | Build A/B service | Allocate capital slices, collect KPIs, automate promotion decision logic | Medium | Shadow Trading | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | Provides quantitative comparison before model cut‑over.
C.1 | Backend | Execution Engine | Core Order Processing | Develop Go service | Consume signals, perform order mapping, send to FIX engine, handle acknowledgements | High | Model Serving, Pre‑trade Risk Engine | 22 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | Primary latency‑critical path; written in Go for rapid development.
C.2 | Backend | Execution Engine | Latency Optimizations | Implement Rust micro‑optimizations | Rewrite hot‑path functions (order book lookup, price calc) in Rust, expose via FFI | Very High | Core Order Processing | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Targets sub‑2 ms order‑to‑FIX latency.
C.3 | Integration | FIX Connectivity | QuickFIX Engine | Integrate QuickFIX | Configure session settings for NSE, Euronext, LSE, handle FIX 4.4 messages | High | Core Order Processing | 6 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | Provides reliable market gateway communication.
C.4 | Backend | Risk Engine | Pre‑trade Checks | Develop Rust service | Validate position limits, exposure caps, sector concentration, margin in <2 ms | High | Core Order Processing | 18 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | Synchronous checks embedded in order path.
C.5 | Backend | Risk Engine | Post‑trade Monitoring | Develop Go service | Compute P&L, drawdown, VaR/CVaR on 15‑min windows, emit alerts | Medium-High | Execution Engine, FIX acknowledgements | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Runs asynchronously; feeds kill‑switch if thresholds breached.
C.6 | Backend | Risk Engine | Kill‑Switch | Implement atomic cancellation | Broadcast cancel all orders, invoke flat‑position routine across venues | High | Post‑trade Monitoring | 10 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | Critical safety net; must be lock‑step across exchanges.
D.1 | QA | Testing | Unit Tests – Ingestion | Write test suite | Validate Kafka producers, schema compliance, DB writes | Medium | Normalization Service | 4 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Automated CI checks to catch data pipeline regressions.
D.2 | QA | Testing | Integration – End‑to‑End Latency | Develop latency tests | Inject synthetic signals, measure signal‑to‑order time across full stack | High | Core Order Processing, Pre‑trade Risk | 6 | 0 | 0 | 0 | 4 | 0 | 16 | 0 | Ensures <20 ms SLA before production rollout.
D.3 | QA | Testing | Performance Benchmarking | Run load tests | Stress Kafka, QuestDB, Redis, execution engine; capture tail latency percentiles | High | All core services | 6 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Validates deterministic latency under peak load.
D.4 | Security | Compliance | Audit Log Validation | Create verification scripts | Check S3 Object Lock configuration, verify immutable logs for risk decisions | Medium | Risk Engine, Logging Stack | 0 | 0 | 0 | 0 | 4 | 12 | 0 | 0 | Supports SEBI/FCA audit requirements.
D.5 | DevOps | Operations | Hyper‑care Support | Create runbooks & monitoring dashboards | Define alerts, on‑call rotations, 90‑day support procedures | Medium | Monitoring Stack, CI/CD | 0 | 0 | 0 | 0 | 12 | 0 | 6 | 0 | Ensures smooth post‑go‑live transition.
| TOTALS | [6 empty] | 198 | 128 | 30 | 74 | 58 | 42 | 48 | 66 | Grand Total: 644 hrs