## Effort Estimation
No | Functionality Type | Module | Feature | Task | Sub Task | Owner Type | Complexity | Estimated Hours | Dependencies | MVP/Future | Tech Remarks | BA Remarks
1 | Authentication & Access Management | Login UI | Email/Password Form | Design login page | Create responsive login form with validation and error handling | Frontend | Medium | 8 | Backend Auth API | MVP | Uses React components; will call Azure Function login endpoint.
2 | Authentication & Access Management | Login UI | Forgot Password | Add forgot password link | Implement UI flow to request password reset email | Frontend | Low | 6 | Backend Auth API | MVP | Calls Azure Function password‑reset; email service mocked for MVP.
3 | Authentication & Access Management | Auth Service | Login Endpoint | Implement Azure Function for login | Validate credentials against Azure AD B2C and issue JWT | Backend | Medium | 12 | Azure AD B2C Configuration | MVP | Node.js 20 runtime; uses MSAL library.
4 | Authentication & Access Management | Auth Service | Token Generation | Create JWT issuance logic | Generate signed JWT with tenant claim | Backend | Low | 8 | Login Endpoint | MVP | Uses Azure Key Vault for signing key.
5 | Infrastructure | Identity | Azure AD B2C Tenant | Provision B2C tenant | Configure user flows, password policies, and custom attributes for tenant isolation | Cloud Infrastructure | Medium-High | 16 |  | MVP | Required for multi‑tenant authentication; performed via Azure portal.
6 | User Experience | Dashboard | Role‑play Home | Build main dashboard UI | Display list of available scenarios, progress metrics, and start button | Frontend | Medium | 14 | Login UI | MVP | React page consuming /scenarios API; uses Azure AD token for auth.
7 | User Experience | Scenario Selector | Scenario List | Implement scenario selection component | Fetch scenarios from backend and allow filter by difficulty | Frontend | Medium | 10 | Dashboard UI | MVP | Calls Azure Functions /scenarios endpoint; pagination for performance.
8 | User Experience | Scenario Selector | Difficulty Level | Add difficulty filter UI | Dropdown to choose level 1‑5; persists selection in session state | Frontend | Low | 6 | Scenario List | MVP | Simple React state management; no backend impact for MVP.
9 | User Experience | Voice Controls | Microphone Button | Create start/stop voice button | Integrate Web Audio API to capture audio streams | Frontend | Medium | 8 | Scenario Selector | MVP | Streams chunks to Azure Speech Service via pre‑signed SAS URL.
10 | Backend Services | Session Management | Start Session API | Create session initiation Function | Allocate session ID, store tenant/associate metadata in Cosmos DB | Backend | Medium | 12 | Azure AD B2C Tenant | MVP | Node.js Azure Function triggered via HTTP; uses Cosmos DB partition key = tenantId.
11 | Backend Services | Audio Streaming | Receive Audio Chunks | Implement chunk ingestion endpoint | Accept base64 audio, forward to Speech‑to‑Text service asynchronously | Backend | Medium-High | 12 | Start Session API | MVP | Uses Azure Service Bus for async processing; stores raw audio in Blob.
12 | Integration | Speech Services | Speech‑to‑Text | Call Azure Speech Service | Send audio chunk, receive transcription, return to processing pipeline | Integration | Medium | 10 | Receive Audio Chunks | MVP | REST call with regional endpoint; handles language model selection.
13 | AI/ML | Prompt Builder | Contextual Prompt Generation | Create prompt construction service | Combine retrieved knowledge snippets with user transcript to build LLM prompt | AI/ML | Medium | 8 | Speech‑to‑Text | MVP | Leverages Azure Cognitive Search results for grounding.
14 | AI/ML | LLM Invocation | Generate AI Response | Call Azure OpenAI Service | Send prompt, receive response text, forward to TTS | AI/ML | Medium-High | 10 | Prompt Builder | MVP | Uses gpt‑4o model; fallback to OpenAI API via config.
15 | Integration | Voice Synthesis | Text‑to‑Speech | Invoke 11 Labs API | Convert AI response text to audio stream for playback | Integration | Medium | 8 | LLM Invocation | MVP | HTTPS POST with API key; cached voices for performance.
16 | Scoring | Feedback Engine | Real‑time Scoring | Develop scoring algorithm | Compare associate response against best‑practice rubric and produce numeric score | Backend | Medium-High | 12 | LLM Invocation | MVP | Rule‑based scoring for MVP; stores thresholds in Cosmos DB.
17 | Data Persistence | Score Storage | Persist Session Results | Write score and metadata to Cosmos DB | Insert document with tenantId, associateId, timestamp, score, scenarioId | Backend | Medium | 8 | Real‑time Scoring | MVP | Uses partition key = tenantId for isolation.
18 | Data Engineering | Blob Storage | Raw Audio Archive | Upload captured audio to Blob | Create container, generate SAS, store files with lifecycle policy | Data Engineering | Low | 6 | Receive Audio Chunks | MVP | Cool tier storage; auto‑tier to Archive after 30 days.
19 | Data Engineering | Blob Storage | Transcripts Archive | Save final transcript files | Write text transcript (JSON) to Blob after STT completes | Data Engineering | Low | 6 | Speech‑to‑Text | MVP | Stored alongside raw audio for audit purposes.
20 | Management | Manager Notes | Add/Update Notes | Create notes API | PUT endpoint to attach manager comments to a session record | Backend | Medium | 8 | Score Storage | MVP | Validated against tenant and associate IDs.
21 | User Experience | Manager Dashboard | View Associate Progress | Build dashboard UI for managers | Display list of associates, scores, practice frequency, and notes | Frontend | Medium | 10 | Score Storage | MVP | Calls /reports API; uses Power BI Embedded for charts.
22 | Analytics | Reporting | Power BI Embedded | Integrate Power BI dashboards | Embed pre‑built reports showing individual and store level metrics | Analytics | Medium-High | 14 | Manager Dashboard | MVP | Shared capacity workspace; authentication via Azure AD token.
23 | Reporting | Export | CSV Export | Create export endpoint | Generate CSV of session data for offline analysis | Integration | Medium | 8 | Score Storage | MVP | Function returns stream; limits to 10,000 rows for MVP.
24 | Infrastructure | Database | Cosmos DB Multi‑Tenant Design | Configure Cosmos DB | Set up database, containers, partition keys, and throughput autoscale | Cloud Infrastructure | Medium-High | 12 |  | MVP | Autoscale starts at 400 RU/s; monitoring for cost control.
25 | Infrastructure | API Management | Tenant Routing Policies | Define policies for multi‑tenant isolation | Add inbound validation, rate limiting, and transformation per tenant | Cloud Infrastructure | Medium-High | 10 | Auth Service | MVP | Developer tier sufficient for pilot; policies stored as named values.
26 | DevOps | CI/CD | Pipeline Setup | Create Azure DevOps pipeline | Build, test, and deploy Functions, Bicep templates, and Frontend SPA | DevOps | Medium | 10 |  | MVP | YAML pipeline with environment variables for dev & prod.
27 | DevOps | IaC | Bicep Templates | Write infrastructure as code | Define resources: Functions, Cosmos DB, API Management, Storage, App Service | DevOps | Medium-High | 12 | Pipeline Setup | MVP | Allows repeatable deployments to other clouds later.
28 | Security | Auth Middleware | Token Validation | Implement JWT validation in Functions | Verify signature, expiration, and tenant claim for each request | Security | Medium | 8 | Login Endpoint | MVP | Uses Azure Functions extensions for HTTP triggers.
29 | Security | RBAC | Role Based Access | Enforce role checks | Differentiate Associate vs Manager vs Admin permissions | Security | Medium | 8 | Token Validation | MVP | Roles stored in Cosmos DB; checked in middleware.
30 | Quality Assurance | Unit Tests | Backend Unit Coverage | Write Jest tests for Functions | Cover auth, session, scoring, and storage functions | QA/Testing | Low | 6 | All backend functions | MVP | Runs in pipeline; target 80% coverage.
31 | Quality Assurance | E2E Tests | Full Role‑play Flow | Create Cypress end‑to‑end tests | Simulate login, start session, speak, receive AI reply, verify score storage | QA/Testing | Medium | 12 | Frontend components, Backend APIs | MVP | Runs against a test tenant; uses mock audio files.
32 | Monitoring | Telemetry | Application Insights | Instrument Functions and SPA | Log request latency, errors, and user interaction events | Monitoring | Low | 6 | All services | MVP | Custom dimensions for tenantId for later analysis.
33 | Monitoring | Alerts | Latency & Error Alerts | Create Azure Monitor alert rules | Notify on >3s response time or >5% error rate | Monitoring | Low | 6 | Telemetry | MVP | Email and Teams channel notifications.
34 | AI/ML | Advanced Scoring | Dynamic Difficulty Adjustment | Implement AI‑driven difficulty scaling | Analyze past scores to auto‑promote scenario difficulty | AI/ML | High | 14 | Real‑time Scoring | Future Phase | Uses Azure Machine Learning model; out of MVP scope.
35 | Content Management | Objection Library | Objection Handling Scenarios | Create CRUD UI for objection templates | Allow admin to add / edit objection scripts per tenant | AI/ML | Medium-High | 12 | Content Upload | Future Phase | Stored in Cosmos DB; UI reuses existing dashboard components.
36 | User Experience | Manager Feedback UI | Enhanced Feedback Form | Add rich text notes and rating option | Enable managers to annotate transcripts with scores and comments | Frontend | Medium | 10 | Manager Dashboard | Future Phase | Will be toggled on via feature flag.
37 | Branding | White‑Label Config | Custom Logo & Theme | Add tenant‑specific branding settings | Load logo URL and color palette from tenant config at runtime | Frontend | Medium | 10 | API Management | Future Phase | Configuration stored in Cosmos DB; applies via CSS variables.
38 | Integration | POS Data Feed | Future POS Integration | Design ingress service for sales data | Create API to receive attach‑rate metrics from client POS system | Integration | High | 12 | Reporting | Future Phase | Will use Service Bus queue; schema TBD after POS details.
| TOTALS | [6 empty] | 368 |  |  | MVP: 310 hrs ¦ Future: 58 hrs