## WBS
No | Functionality Type | Module | Task | Sub-tasks | Features | Interface Type | Frontend | Backend | AI/ML | DevOps | Cloud | Mobile | QA | Security | Estimated Hours | Is MVP | Complexity | Tech Remarks | BA Remarks
A.1.1 | User Authentication & Access Control | Microsoft SSO Integration | Configure Azure AD SAML/OIDC SSO | • Set up Azure AD application registration • Configure SAML/OIDC metadata exchange • Define SSO callback endpoints • Test SSO flow with mock user accounts | Enables Single Sign-On via Azure AD using SAML/OIDC protocols, allowing users to authenticate seamlessly with their Microsoft credentials. | Backend + Security |  | ✓ |  |  | ✓ |  | ✓ | ✓ | 16 | Yes | High | Azure AD SAML/OIDC configuration; JWT token validation for session management.
A.1.2 | User Authentication & Access Control | Microsoft SSO Integration | Implement SSO session management | • Store SSO session tokens securely • Handle token expiration and refresh • Implement session invalidation on logout • Log SSO events for audit purposes | Manages user sessions post-SSO authentication, including token storage, refresh, and secure logout with audit logging. | Backend + Security |  | ✓ |  |  | ✓ |  | ✓ | ✓ | 12 | Yes | Medium | Secure token storage in HTTP-only cookies; Azure AD token refresh logic.
A.2.1 | User Authentication & Access Control | Role-Based Access Control (RBAC) | Define Cosmos DB RBAC roles | • Map business roles to Cosmos DB permissions • Configure role inheritance hierarchy • Set up role assignment rules • Test role-based data access | Defines and configures role-based access control in Cosmos DB, ensuring users can only access data permitted by their role. | Backend + Security |  | ✓ |  |  | ✓ |  | ✓ | ✓ | 12 | Yes | Medium | Cosmos DB role-based permissions; Azure AD Conditional Access integration.
A.2.2 | User Authentication & Access Control | Role-Based Access Control (RBAC) | Implement Azure AD Conditional Access | • Configure Conditional Access policies in Azure AD • Define access rules based on user attributes • Test policy enforcement with different user roles • Log access attempts for compliance | Enforces Conditional Access policies in Azure AD, restricting access based on user roles, locations, and other attributes. | Backend + Security |  | ✓ |  |  | ✓ |  | ✓ | ✓ | 16 | Yes | High | Azure AD Conditional Access policies; integration with Cosmos DB RBAC.
A.2.3 | User Authentication & Access Control | Role-Based Access Control (RBAC) | Audit logging for RBAC actions | • Log role assignments and changes • Track data access attempts • Store logs in a secure, immutable format • Set up log retention policies | Logs all RBAC-related actions, including role assignments and data access attempts, for compliance and auditing purposes. | Backend + Security |  | ✓ |  |  | ✓ |  | ✓ | ✓ | 8 | Yes | Medium | Azure Monitor or Log Analytics for log storage; immutable log retention.
B.1.1 | Document Ingestion & Processing | Document OCR Pipeline | Set up Azure Document Intelligence service | • Create Azure Document Intelligence resource in the cloud • Configure API access and authentication • Set up rate limiting and throttling policies • Test basic OCR functionality with sample PDFs | Provisions the Azure Document Intelligence service with proper authentication and rate limiting for OCR processing. | Backend + Cloud |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 8 | Yes | Medium | Azure Document Intelligence API with rate limiting to handle API constraints.
B.1.2 | Document Ingestion & Processing | Document OCR Pipeline | Implement PDF ingestion and OCR processing | • Build backend service to ingest PDFs from repositories • Integrate Azure Document Intelligence for OCR processing • Handle duplicate PDF detection and naming conflicts • Log ingestion events for auditability | Processes PDFs through Azure Document Intelligence OCR, detects duplicates, and logs ingestion events for compliance. | Backend + AI/ML |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 16 | Yes | High | Azure Document Intelligence for OCR; duplicate detection via checksum comparison.
B.1.3 | Document Ingestion & Processing | Document OCR Pipeline | Optimize OCR quality for scanned manuals | • Test OCR accuracy with various scanned manuals • Adjust preprocessing settings for better text extraction • Implement fallback mechanisms for low-confidence OCR results • Document OCR quality metrics and thresholds | Improves OCR accuracy for scanned manuals by tuning preprocessing and implementing fallback mechanisms. | Backend + AI/ML |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 12 | Yes | Medium | Preprocessing includes image enhancement and layout analysis for better OCR results.
B.2.1 | Document Ingestion & Processing | Vector Search Indexing | Set up Azure Cognitive Search service | • Create Azure Cognitive Search resource in the cloud • Configure indexing and vector search capabilities • Set up security and access control for the search service • Test basic vector search functionality | Provisions the Azure Cognitive Search service with vector search capabilities and proper security controls. | Backend + Cloud |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 8 | Yes | Medium | Azure Cognitive Search with vector indexing for semantic search capabilities.
B.2.2 | Document Ingestion & Processing | Vector Search Indexing | Implement vector search indexing for OCR-processed documents | • Transform OCR-processed text into vector embeddings • Index vector embeddings in Azure Cognitive Search • Implement search API for retrieving relevant document fragments • Optimize search performance and relevance | Indexes OCR-processed documents as vector embeddings and provides a search API for retrieving relevant fragments. | Backend + AI/ML |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 20 | Yes | High | Vector embeddings generated using Azure AI; search optimized for relevance and performance.
B.2.3 | Document Ingestion & Processing | Vector Search Indexing | Handle API rate limits and throttling | • Monitor API usage and enforce rate limits • Implement retry logic for throttled requests • Log API usage metrics for analysis • Optimize batch processing to minimize API calls | Manages API rate limits and throttling to ensure reliable document ingestion and retrieval within constraints. | Backend + Cloud |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 12 | Yes | Medium | Rate limiting and retry logic to handle Azure API constraints.
C.1.1 | AI Coaching Engine | AI Coaching Engine | Set up Azure OpenAI Service with GPT-4o | • Create Azure OpenAI resource in the cloud • Configure GPT-4o model deployment • Set up API endpoints for coaching interactions • Implement rate limiting and quota management | Azure OpenAI Service is deployed with GPT-4o configured for coaching interactions, including API endpoints and rate limiting. | Backend + AI/ML + Cloud |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 16 | Yes | High | Azure OpenAI Service with GPT-4o; API rate limiting to manage costs and compliance.
C.1.2 | AI Coaching Engine | AI Coaching Engine | Implement vector search for document retrieval | • Set up vector database for document fragments • Index approved company documentation • Implement search API for retrieving relevant fragments • Handle duplicate PDFs and naming conflicts | Vector search capability is implemented to retrieve relevant document fragments, handling duplicates and naming conflicts. | Backend + AI/ML + Cloud |  | ✓ | ✓ |  | ✓ |  | ✓ |  | 20 | Yes | High | Vector database for semantic search; duplicate handling via content hashing.
C.1.3 | AI Coaching Engine | AI Coaching Engine | Develop AI mood simulation for coaching | • Design mood states (impatient, negotiating, etc.) • Implement dynamic mood transitions in dialogue • Integrate mood simulation with coaching responses • Test for realistic and compliant behavior | AI coach simulates different moods (impatient, negotiating) and evaluates associate responses for confidence, empathy, and compliance. | Backend + AI/ML |  | ✓ | ✓ |  |  |  | ✓ |  | 24 | Yes | High | GPT-4o fine-tuning for mood simulation; compliance checks to avoid hallucinations.
C.2.1 | AI Coaching Engine | Human-in-the-Loop Approval | Design Durable Functions for approval workflow | • Define approval workflow states and transitions • Set up Durable Functions orchestration • Implement role-based access control for approvers • Log all approval actions for auditability | Durable Functions orchestrate the approval workflow for AI-generated coaching feedback, with role-based access and audit logging. | Backend + Security |  | ✓ |  |  | ✓ |  | ✓ | ✓ | 16 | Yes | Medium | Azure Durable Functions for workflow; RBAC and audit logs for compliance.
C.2.2 | AI Coaching Engine | Human-in-the-Loop Approval | Integrate approval workflow with AI coaching engine | • Connect AI-generated feedback to approval workflow • Implement status tracking for feedback items • Set up notifications for pending approvals • Ensure retention policies for approved/rejected feedback | AI-generated coaching feedback is routed through the approval workflow, with status tracking, notifications, and retention policies enforced. | Backend + Security |  | ✓ |  |  | ✓ |  | ✓ | ✓ | 12 | Yes | Medium | Workflow integration with AI engine; retention policies for compliance.
D.1.1 | Analytics & Reporting | Power BI Dashboards | Design Power BI dashboard layout | • Create wireframes for onboarding completion view • Design regional performance comparison layout • Define competency score visualization components • Set up color schemes and branding guidelines | Interactive dashboard layout showing onboarding completion, regional performance metrics, and competency scores with drill-down capabilities. | Frontend | ✓ | [5 empty] | ✓ |  | 12 | Yes | Medium | Power BI Desktop for design; responsive layout for different screen sizes
D.1.2 | Analytics & Reporting | Power BI Dashboards | Develop backend API for dashboard data | • Create API endpoints for onboarding metrics • Implement regional performance data aggregation • Build competency score calculation service • Add caching layer for frequently accessed data | RESTful API providing filtered and aggregated data for Power BI visualizations, with caching for performance optimization. | Backend |  | ✓ |  |  | ✓ |  | ✓ |  | 20 | Yes | High | Azure Functions for serverless API; Redis for caching; data aggregation optimized for Power BI
D.1.3 | Analytics & Reporting | Power BI Dashboards | Implement role-based access control | • Configure Power BI row-level security • Map organizational roles to dashboard views • Test access restrictions for different user types • Document security configuration | Dashboard access controlled by user roles, with different views for executives, managers, and associates. | Frontend + Backend | ✓ | ✓ |  |  | ✓ |  | ✓ | ✓ | 16 | Yes | Medium | Azure Active Directory integration for role mapping; Power BI embedded for secure dashboard delivery
D.2.1 | Analytics & Reporting | Weekly PDF Reports | Design PDF report template | • Create layout for executive summary section • Design regional performance tables • Add visual elements for key metrics • Define corporate branding elements | Professional PDF template with standardized sections for weekly reports, including tables, charts, and executive summaries. | Backend |  | ✓ |  |  |  |  | ✓ |  | 8 | Yes | Low | PDF template designed for Azure Logic Apps; compatible with Power BI data exports
D.2.2 | Analytics & Reporting | Weekly PDF Reports | Implement Logic Apps workflow | • Configure data extraction from Power BI • Set up PDF generation process • Implement email distribution logic • Add error handling and retry mechanisms | Automated workflow that extracts data, generates PDF reports, and distributes them via email every Monday morning. | Backend + DevOps |  | ✓ |  | ✓ | ✓ |  | ✓ |  | 24 | Yes | High | Azure Logic Apps for workflow automation; Power Automate for email distribution
D.2.3 | Analytics & Reporting | Weekly PDF Reports | Set up monitoring and alerts | • Configure success/failure logging • Set up email alerts for workflow failures • Create dashboard for report generation status • Implement retry logic for transient failures | Monitoring system that tracks report generation status and alerts administrators of any failures in the process. | DevOps |  |  |  | ✓ | ✓ |  | ✓ |  | 12 | Yes | Medium | Azure Monitor for logging; Logic Apps built-in monitoring capabilities
E.1.1 | Mobile & Web Interface | React Web Interface | Setup React 18 project with Azure Front Door CDN | • Initialize React 18 project with Vite • Configure Azure Front Door for CDN and caching • Set up environment variables for different deployment stages • Implement basic routing structure | A React 18 project configured with Azure Front Door CDN for optimized content delivery and caching. | Web+Cloud | ✓ |  |  |  | ✓ |  | ✓ |  | 8 | Yes | Medium | Using Vite for React 18 setup; Azure Front Door for CDN and caching.
E.1.2 | Mobile & Web Interface | React Web Interface | Implement responsive UI components | • Design and develop reusable UI components • Ensure components are responsive across devices • Integrate with design system if available • Test components for accessibility compliance | A set of responsive UI components that work across different screen sizes and devices. | Web | ✓ | [5 empty] | ✓ |  | 12 | Yes | Medium | Using CSS-in-JS for styling; ensuring WCAG 2.1 AA compliance.
E.1.3 | Mobile & Web Interface | React Web Interface | Integrate Microsoft SSO | • Set up Microsoft Identity Platform for authentication • Implement login/logout flows in React • Handle token storage and session management • Test SSO integration across different browsers | Microsoft SSO integration allowing users to log in using their corporate credentials. | Web+Backend | ✓ | ✓ |  |  |  |  | ✓ | ✓ | 16 | Yes | High | Using MSAL.js for Microsoft SSO integration; secure token storage in HTTP-only cookies.
E.2.1 | Mobile & Web Interface | React Native Mobile App | Setup React Native (Expo) project | • Initialize React Native project with Expo • Configure Expo for iOS and Android builds • Set up environment variables for different deployment stages • Implement basic navigation structure | A React Native project configured with Expo for cross-platform mobile development. | Mobile |  |  |  |  | ✓ | ✓ | ✓ |  | 8 | Yes | Medium | Using Expo for React Native setup; configuring for both iOS and Android.
E.2.2 | Mobile & Web Interface | React Native Mobile App | Implement offline-first UI components | • Design and develop reusable UI components for mobile • Ensure components work offline with local data caching • Implement synchronization logic for when connectivity is restored • Test components for different screen sizes and orientations | Offline-first UI components that cache data locally and synchronize when connectivity is restored. | Mobile |  |  |  |  | ✓ | ✓ | ✓ |  | 16 | Yes | High | Using AsyncStorage for local caching; implementing background sync for data synchronization.
E.2.3 | Mobile & Web Interface | React Native Mobile App | Integrate Microsoft SSO for mobile | • Set up Microsoft Identity Platform for mobile authentication • Implement login/logout flows in React Native • Handle token storage and session management securely • Test SSO integration on both iOS and Android devices | Microsoft SSO integration allowing mobile users to log in using their corporate credentials. | Mobile+Backend |  | ✓ |  |  |  | ✓ | ✓ | ✓ | 16 | Yes | High | Using Expo AuthSession for Microsoft SSO integration; secure token storage in Keychain/Keystore.
F.1.1 | Integration & Workflow Orchestration | LMS Integration | Design Logic Apps workflow for SCORM/xAPI export | • Map data fields between system and LMS • Define triggers for export events • Configure error handling and retries • Set up logging for audit trails | Logic Apps workflow that exports training data to LMS in SCORM/xAPI format with error handling and logging. | Backend + DevOps |  | ✓ |  | ✓ | ✓ |  | ✓ |  | 16 | Yes | Medium | Azure Logic Apps with SCORM/xAPI connectors; retry policy for transient failures
F.1.2 | Integration & Workflow Orchestration | LMS Integration | Implement authentication for LMS API | • Configure OAuth2 client credentials • Store secrets in Azure Key Vault • Implement token refresh logic • Test API connectivity | Secure authentication flow for LMS API using OAuth2 with token management via Azure Key Vault. | Backend + DevOps |  | ✓ |  | ✓ | ✓ |  | ✓ | ✓ | 8 | Yes | Medium | OAuth2 client credentials flow; Azure Key Vault for secret management
F.1.3 | Integration & Workflow Orchestration | LMS Integration | Create monitoring dashboard for LMS exports | • Design dashboard layout in Azure Monitor • Configure alerts for failed exports • Set up success/failure metrics • Implement export latency tracking | Azure Monitor dashboard showing LMS export status, success rates, and latency metrics with alerting. | Backend + DevOps |  | ✓ |  | ✓ | ✓ |  | ✓ |  | 12 | Yes | Medium | Azure Monitor with custom metrics; alert rules for export failures
F.2.1 | Integration & Workflow Orchestration | Voice-to-Text Fallback | Implement Azure Speech Service integration | • Set up Azure Speech resource • Configure speech-to-text endpoint • Implement fallback detection logic • Handle connectivity error scenarios | Azure Speech Service integration with automatic fallback to text input when voice connectivity is poor. | Mobile + Backend |  | ✓ | ✓ |  | ✓ | ✓ | ✓ |  | 16 | Yes | High | Azure Speech Service with custom fallback logic; network detection for connectivity issues
F.2.2 | Integration & Workflow Orchestration | Voice-to-Text Fallback | Develop mobile UI for fallback mode | • Design fallback notification UI • Implement text input alternative • Add connectivity status indicator • Test UI responsiveness | Mobile UI that shows voice-to-text fallback status and provides text input alternative when needed. | Mobile | [5 empty] | ✓ | ✓ |  | 8 | Yes | Medium | React Native for cross-platform mobile UI; connectivity status detection
F.2.3 | Integration & Workflow Orchestration | Voice-to-Text Fallback | Create backend service for fallback coordination | • Build API endpoint for fallback requests • Implement session state management • Add logging for fallback events • Configure retry logic for voice reconnection | Backend service that coordinates voice-to-text fallback with session management and retry logic. | Backend |  | ✓ |  |  | ✓ |  | ✓ |  | 12 | Yes | Medium | REST API with session state; exponential backoff for voice reconnection attempts
G.1.1 | Infrastructure & DevOps | Azure Infrastructure Setup | Provision Azure Resource Group | • Create resource group in Azure portal • Configure naming conventions and tags • Set up resource locks to prevent accidental deletion • Assign initial RBAC roles | Creates a dedicated Azure Resource Group with standardized naming and initial access controls for all project resources. | DevOps + Cloud |  |  |  | ✓ | ✓ |  | ✓ | ✓ | 4 | Yes | Low | Azure Resource Manager templates for consistent provisioning
G.1.2 | Infrastructure & DevOps | Azure Infrastructure Setup | Configure Azure Kubernetes Service (AKS) | • Deploy AKS cluster with node pools • Configure network policies and ingress controllers • Set up monitoring and logging integration • Implement cluster autoscaling | Deploys a production-ready AKS cluster with monitoring, logging, and autoscaling capabilities for containerized workloads. | DevOps + Cloud |  |  |  | ✓ | ✓ |  | ✓ | ✓ | 16 | Yes | High | AKS with Azure Monitor integration and network policies for security
G.1.3 | Infrastructure & DevOps | Azure Infrastructure Setup | Set up Azure Storage Accounts | • Create storage accounts for different data types • Configure blob containers with appropriate access tiers • Set up lifecycle management policies • Implement storage encryption | Provisions secure Azure Storage Accounts with lifecycle management and encryption for document storage and retrieval. | DevOps + Cloud |  |  |  | ✓ | ✓ |  | ✓ | ✓ | 8 | Yes | Medium | Azure Blob Storage with lifecycle policies and encryption at rest
G.2.1 | Infrastructure & DevOps | Audit Logging & Compliance | Configure Azure Monitor Log Analytics | • Set up Log Analytics workspace • Configure diagnostic settings for Azure resources • Create custom log queries for compliance monitoring • Set up alerts for suspicious activities | Configures Azure Monitor Log Analytics to collect and analyze logs from all Azure resources with custom queries for compliance monitoring. | DevOps + Security |  |  |  | ✓ | ✓ |  | ✓ | ✓ | 12 | Yes | Medium | Azure Monitor Log Analytics with custom KQL queries for compliance
G.2.2 | Infrastructure & DevOps | Audit Logging & Compliance | Implement Azure Purview for Data Governance | • Set up Azure Purview account • Configure data sources and scanning • Create data classification and labeling policies • Set up access policies and retention rules | Implements Azure Purview to scan, classify, and govern data with retention policies and access controls for compliance. | DevOps + Security |  |  |  | ✓ | ✓ |  | ✓ | ✓ | 16 | Yes | High | Azure Purview with automated data scanning and classification
G.2.3 | Infrastructure & DevOps | Audit Logging & Compliance | Set up Role-Based Access Control (RBAC) | • Define custom roles based on job functions • Assign roles to users and groups • Configure access reviews and attestation • Set up conditional access policies | Implements RBAC with custom roles, access reviews, and conditional access policies to enforce least privilege access. | DevOps + Security |  |  |  | ✓ | ✓ |  | ✓ | ✓ | 8 | Yes | Medium | Azure RBAC with conditional access and access reviews