## Effort Estimation
No | Functionality Type | Module | Feature | Task | Sub Task | Complexity | Dependencies | Frontend (hrs) | Backend (hrs) | Cloud Infrastructure (hrs) | DevOps (hrs) | Security (hrs) | QA (hrs) | Tech Remarks | BA Remarks
A.0 | Project Setup | Repository | Monorepo & CI/CD init | Initialize repo | Create GitHub repo, set up branch protection, initialize Vite React project | Medium-High |  | 0 | 0 | 0 | 12 | 0 | 0 | CI/CD pipeline foundation; ensures consistent builds and automated deployments.
A.1 | Project Setup | Azure Resources | Provision core services | Create Cosmos DB, Functions, Static Web Apps | Use Azure CLI/Portal to provision serverless resources, configure connection strings | Medium-High |  | 0 | 0 | 12 | 0 | 0 | 0 | Sets up the serverless backbone; all subsequent work depends on these resources.
B.0 | Authentication | Authentication | Azure AD B2C setup | Configure B2C tenant | Create user flows, set up policies for email/social login, enable anonymous access | Medium |  | 0 | 0 | 8 | 0 | 0 | 0 | Provides secure, low‑maintenance identity management without custom auth code.
B.1 | Authentication | Authentication | Login UI | Build login page | Design form, validation, error handling, forgot password link | Medium | B.0 | 10 | 0 | 0 | 0 | 0 | 4 | Mobile‑first login screen; validates credentials against B2C and stores JWT.
B.2 | Authentication | Authentication | API Integration | Connect frontend to B2C | Implement token acquisition, store JWT, handle logout flow | Medium | B.0,B.1 | 2 | 8 | 0 | 0 | 2 | 2 | Ensures secure session handling; minimal backend work as token validation is delegated to B2C.
C.0 | User Interface | UI | Core Layout | Design mobile navigation | Implement responsive header, bottom navigation, theming | Medium | B.1 | 14 | 0 | 0 | 0 | 0 | 4 | Foundation for all screens; optimized for thumb reach and low‑bandwidth devices.
C.1 | User Interface | UI | Questionnaire UI | Integrate SurveyJS | Configure SurveyJS model, branching logic, display questions | Medium-High | C.0 | 12 | 0 | 0 | 0 | 0 | 4 | Leverages client‑side branching; reduces server load and keeps latency low.
C.2 | User Interface | UI | Language Switcher | Add i18n toggle | Implement react-i18next, language resources, UI toggle | Medium | C.1 | 8 | 0 | 0 | 0 | 0 | 2 | Supports English/Spanish without page reload; key for 20‑25% Spanish users.
C.3 | User Interface | UI | Accessibility | Large button design | Apply ARIA labels, high‑contrast colors, focus management | Low | C.0 | 6 | 0 | 0 | 0 | 0 | 2 | Ensures usability for low‑literacy and senior patients on small screens.
D.0 | Backend | Backend API | Submit Endpoint | Create HTTP POST function | Receive questionnaire JSON, return success status | Medium | B.2 | 0 | 10 | 0 | 0 | 0 | 4 | Stateless Azure Function; minimal latency for mobile clients.
D.1 | Backend | Backend API | Validation | Validate input data | Schema check, required fields, value ranges | Medium | D.0 | 0 | 8 | 0 | 0 | 0 | 2 | Prevents malformed or malicious payloads before storage.
D.2 | Backend | Backend API | Data Persistence | Store response in Cosmos DB | Insert document, handle errors, create index for queries | Medium | D.1 | 0 | 6 | 0 | 0 | 0 | 2 | Serverless document store; supports JSON natively and complies with HIPAA when BAA is enabled.
D.3 | Backend | Backend Service | Guidance Engine | Evaluate rules | Apply conditional logic, generate non‑diagnostic suggestions | Medium | D.2 | 0 | 8 | 0 | 0 | 0 | 2 | Rule‑based, no ML model; ensures compliance by avoiding diagnostic language.
D.4 | Backend | Backend Service | PDF Generation | Create printable PDF | Render response to PDF, provide download link for staff | Medium | D.2 | 0 | 6 | 0 | 0 | 0 | 2 | Supports legacy paper workflow by allowing staff to print/export completed forms.
E.0 | Cloud Infrastructure | Monitoring | Application Insights | Enable monitoring | Instrument Functions, set up alerts for errors and latency | Low |  | 0 | 0 | 8 | 2 | 0 | 2 | Provides real‑time telemetry; essential for low‑maintenance operations.
E.1 | Cloud Infrastructure | Compliance Auditing | Azure Policy enforcement | Apply security policies | Enforce encryption at rest, logging, access reviews via Azure Policy | Medium | E.0 | 0 | 0 | 6 | 0 | 4 | 2 | Ensures HIPAA‑compatible configuration and auditability.
F.0 | DevOps | CI/CD Pipeline | GitHub Actions configuration | Configure build, test, deploy workflow | Build React SPA, deploy to Azure Static Web Apps, deploy Functions | Medium | A.0 | 0 | 0 | 0 | 12 | 0 | 0 | Automates repeatable deployments; reduces manual errors.
F.1 | DevOps | Automated Tests | Run test suites in pipeline | Execute Jest & Cypress | Run unit and integration tests, fail build on errors | Low | F.0 | 0 | 0 | 0 | 4 | 0 | 8 | Ensures code quality on every push; gates production releases.
G.0 | Security | Encryption | TLS & at‑rest encryption | Configure secure communication | Enable HTTPS for Function endpoints, ensure Cosmos DB encryption | Medium | E.1 | 0 | 0 | 2 | 0 | 8 | 0 | Protects PHI in transit and storage, meeting compliance requirements.
G.1 | Security | RBAC | Role‑Based Access Control | Define role assignments | Assign Function app roles, Cosmos DB permissions for least‑privilege access | Medium | G.0 | 0 | 0 | 2 | 0 | 8 | 0 | Limits user and service privileges, reducing attack surface.
H.0 | QA | Unit Tests | Component testing | Write unit tests for UI components | Test React components, form validation, language toggle | Low | C.1 | 0 | 0 | 0 | 0 | 0 | 10 | Catches regressions early; ensures core UI works across languages.
H.1 | QA | Integration Tests | API validation | Test backend endpoints | Validate request/response flow for submission, storage, and guidance generation | Medium | D.3 | 0 | 0 | 0 | 0 | 0 | 10 | Ensures end‑to‑end correctness of data pipeline.
H.2 | QA | E2E Tests | Mobile user flow | Simulate complete patient journey | Cypress tests covering login, questionnaire branching, PDF download, language switch | Medium-High | C.2,H.0,H.1 | 0 | 0 | 0 | 0 | 0 | 12 | Validates real‑world mobile experience; catches UI/UX issues for low‑literacy users.
I.0 | Documentation | Documentation | Staff User Guide | Write usage instructions | Explain questionnaire flow, printing PDF, admin portal access | Low |  | 2 | 2 | 0 | 0 | 0 | 2 | Facilitates transition from paper to digital; reduces training overhead.
I.1 | Documentation | Documentation | Deployment Guide | Document CI/CD steps | Outline environment variables, resource provisioning, monitoring setup | Low | F.0 | 0 | 0 | 2 | 4 | 0 | 2 | Ensures future maintainers can redeploy and scale the solution reliably.
| TOTALS | [6 empty] | 54 | 48 | 40 | 34 | 22 | 78 | Grand Total: 276 hrs