## WBS
No | Functionality Type | Module | Task | Sub-tasks | Features | Interface Type | Frontend | Backend | AI/ML | DevOps | Cloud | Complexity | Tech Remarks | BA Remarks
A.1.1 | User Management & Authentication | Authentication Flow | Configure Azure AD B2C tenant | • Set up Azure AD B2C tenant with multi-tenant support • Configure custom policies for user flows • Enable SSO with identity providers • Set up tenant isolation for partner accounts | Azure AD B2C tenant configured with multi-tenant support and custom policies for user authentication flows. | Cloud |  |  |  | ✓ | ✓ |  | Azure AD B2C with custom policies for multi-tenant isolation and SSO.
A.1.2 | User Management & Authentication | Authentication Flow | Implement login UI with Azure AD B2C | • Design login form with Azure AD B2C integration • Handle authentication callbacks and token storage • Implement error handling for authentication failures • Style UI to match white-label branding | Login UI integrated with Azure AD B2C, handling authentication callbacks and token storage securely. | Web | ✓ | [5 empty] | React 18 with TypeScript, using MSAL.js for Azure AD B2C integration.
A.1.3 | User Management & Authentication | Authentication Flow | Backend token validation middleware | • Create middleware to validate JWT tokens • Implement token refresh logic • Handle token expiration and revocation • Log authentication events for audit | Middleware to validate JWT tokens issued by Azure AD B2C, handling refresh and expiration logic. | Backend |  | ✓ |  |  |  |  | Azure Functions (Node.js) with JWT validation using MSAL library.
A.2.1 | User Management & Authentication | Role-Based Access Control | Define RBAC policies in Azure AD B2C | • Create custom roles for managers and associates • Configure role assignment rules • Set up role-based access policies • Test role inheritance and permissions | Custom roles and policies defined in Azure AD B2C for tenant-aware access control. | Cloud |  |  |  | ✓ | ✓ |  | Azure AD B2C custom policies with role-based access control.
A.2.2 | User Management & Authentication | Role-Based Access Control | Backend RBAC enforcement | • Implement role checks in API endpoints • Handle unauthorized access attempts • Log access control events • Integrate with Azure AD B2C role claims | Backend enforcement of RBAC policies, validating role claims from Azure AD B2C tokens. | Backend |  | ✓ |  |  |  |  | Azure Functions (Node.js) with role validation using MSAL and custom middleware.
A.2.3 | User Management & Authentication | Role-Based Access Control | Tenant isolation in Cosmos DB | • Configure Cosmos DB for multi-tenant data isolation • Implement tenant ID partitioning • Set up access policies per tenant • Test data isolation and access control | Cosmos DB configured for multi-tenant data isolation with tenant-specific access policies. | Backend + Cloud |  | ✓ |  |  | ✓ |  | Azure Cosmos DB with tenant ID partitioning and access policies.
B.1.1 | AI Conversation Engine | LLM Integration | Set up Azure OpenAI Service connection | • Create Azure OpenAI resource in the Azure portal • Configure API keys and permissions for secure access • Set up deployment for GPT-4o mini model • Implement token-based authentication for API calls | Establishes a secure connection to Azure OpenAI Service with GPT-4o mini model deployment, enabling API access for conversational AI responses. | Backend + AI/ML + Cloud |  | ✓ | ✓ |  | ✓ |  | Azure OpenAI Service with GPT-4o mini for cost-effective inference; token-based authentication for secure API access.
B.1.2 | AI Conversation Engine | LLM Integration | Implement conversational AI endpoint | • Design API endpoint for handling conversation requests • Integrate Azure OpenAI Service for generating responses • Implement request/response logging for debugging • Add input validation and error handling | Backend API endpoint that processes user input, generates AI responses using Azure OpenAI, and logs interactions for debugging. | Backend + AI/ML |  | ✓ | ✓ |  |  |  | Azure Functions (Node.js 20) for serverless API; structured logging for debugging and compliance.
B.1.3 | AI Conversation Engine | LLM Integration | Configure fine-tuning pipeline | • Set up Azure AI Studio for fine-tuning workflows • Prepare training data in required format • Configure fine-tuning job parameters • Deploy fine-tuned model to Azure OpenAI Service | Fine-tunes the GPT-4o mini model using Azure AI Studio to improve response quality for sales training scenarios. | AI/ML + Cloud |  |  | ✓ |  | ✓ |  | Azure AI Studio for fine-tuning; GPT-4o mini as base model for cost efficiency.
B.2.1 | AI Conversation Engine | Voice Synthesis | Set up ElevenLabs API integration | • Register for ElevenLabs API and obtain credentials • Configure API client in backend service • Implement voice synthesis request handling • Set up error handling for API failures | Integrates ElevenLabs API for voice synthesis, enabling text-to-speech conversion for role-play scenarios. | Backend + Cloud |  | ✓ |  |  | ✓ |  | ElevenLabs API for voice synthesis; Azure Functions for backend integration.
B.2.2 | AI Conversation Engine | Voice Synthesis | Implement voice response endpoint | • Design API endpoint for voice synthesis requests • Integrate ElevenLabs API for generating voice responses • Implement audio streaming or file return logic • Add logging for voice synthesis requests | Backend API endpoint that converts text responses to voice using ElevenLabs and returns audio to the client. | Backend |  | ✓ |  |  |  |  | ElevenLabs API for voice synthesis; Azure Functions for serverless endpoint.
C.1.1 | Content Ingestion & Management | Document Processing | Set up Azure Form Recognizer | • Create Azure Form Recognizer resource in Azure portal • Configure prebuilt models for PDF and PPT parsing • Set up API keys and authentication for secure access • Test basic document extraction with sample files | Azure Form Recognizer resource configured with prebuilt models for parsing PDF and PPT files, ready for integration with the backend. | Backend+Cloud |  | ✓ | ✓ |  | ✓ |  | Using Azure Form Recognizer prebuilt models for initial document parsing to minimize custom development.
C.1.2 | Content Ingestion & Management | Document Processing | Integrate Azure AI Document Intelligence | • Set up Azure AI Document Intelligence resource • Configure custom document processing pipeline • Implement document classification and key-value extraction • Test with sample training materials | Azure AI Document Intelligence pipeline configured to classify and extract structured data from training materials, integrated with the backend. | Backend+AI Service+Cloud |  | ✓ | ✓ |  | ✓ |  | Using Azure AI Document Intelligence for advanced document processing to enhance data extraction accuracy.
C.1.3 | Content Ingestion & Management | Document Processing | Build document processing API | • Create Azure Function for document upload and processing • Implement error handling and retry logic • Set up logging and monitoring for document processing • Integrate with Azure Cognitive Search for indexing | Azure Function API that processes uploaded documents, extracts data, and indexes it in Azure Cognitive Search for retrieval. | Backend+Cloud |  | ✓ | ✓ |  | ✓ |  | Using Azure Functions for serverless document processing to handle variable workloads efficiently.
C.2.1 | Content Ingestion & Management | Content Storage | Configure Azure Blob Storage | • Create Azure Blob Storage account with Hot tier • Set up containers for different content types (PDFs, PPTs, images) • Configure access policies and SAS tokens for secure uploads • Implement lifecycle management for cost optimization | Azure Blob Storage configured with containers for different content types, secure access policies, and lifecycle management for cost efficiency. | Backend+Cloud |  | ✓ |  |  | ✓ |  | Using Azure Blob Storage Hot tier for frequently accessed training materials to ensure low-latency retrieval.
C.2.2 | Content Ingestion & Management | Content Storage | Implement content upload API | • Create Azure Function for handling file uploads • Implement file validation and size checks • Generate unique identifiers for uploaded content • Store metadata in Cosmos DB for tracking | Azure Function API that handles file uploads, validates content, stores files in Blob Storage, and tracks metadata in Cosmos DB. | Backend+Cloud |  | ✓ |  |  | ✓ |  | Using Azure Functions for serverless file upload handling to scale with demand and reduce operational overhead.
C.2.3 | Content Ingestion & Management | Content Storage | Set up content retrieval API | • Create Azure Function for retrieving content by ID • Implement access control for tenant isolation • Add caching layer for frequently accessed content • Integrate with Azure CDN for faster delivery | Azure Function API that retrieves content from Blob Storage with tenant isolation, caching, and CDN integration for fast delivery. | Backend+Cloud |  | ✓ |  |  | ✓ |  | Using Azure CDN to cache and deliver frequently accessed training materials with low latency.
D.1.1 | Scoring & Feedback System | Scoring Engine | Design scoring rule schema | • Define JSON schema for scoring rules • Create validation logic for rule inputs • Document rule configuration examples • Implement schema versioning for future updates | A JSON schema that defines configurable scoring rules for performance evaluation, including validation and versioning support. | Backend |  | ✓ | ✓ |  |  |  | JSON Schema with Ajv validation; versioning via semantic versioning in schema metadata.
D.1.2 | Scoring & Feedback System | Scoring Engine | Implement scoring microservice | • Set up Azure Function for scoring logic • Integrate LangChain for rule evaluation • Implement token-based authentication • Add logging for audit trails | A serverless microservice that evaluates performance based on configurable rules and returns scores with audit logging. | Backend+Cloud |  | ✓ | ✓ |  | ✓ |  | Azure Functions (Node.js 20) with LangChain; JWT authentication via Azure AD B2C.
D.1.3 | Scoring & Feedback System | Scoring Engine | Build feedback generation logic | • Design feedback templates • Integrate LLM for dynamic feedback • Implement feedback scoring correlation • Add localization support for feedback | Generates dynamic feedback based on scores and performance, with support for multiple languages. | Backend+AI Service |  | ✓ | ✓ |  |  |  | Azure OpenAI Service (GPT-4o mini) for feedback generation; feedback templates stored in Cosmos DB.
D.2.1 | Scoring & Feedback System | Transcript Storage | Set up Cosmos DB container | • Define partition key strategy • Configure throughput (RU/s) • Implement tenant isolation • Set up backup policy | A Cosmos DB container optimized for storing role-play transcripts and scores with tenant isolation and automated backups. | Backend+Cloud |  | ✓ |  |  | ✓ |  | Partition key: tenantId; RU/s: 1000 for MVP; backup policy: daily snapshots.
D.2.2 | Scoring & Feedback System | Transcript Storage | Implement transcript storage API | • Create API endpoints for CRUD operations • Add tenant-based access control • Implement data validation • Set up indexing for query performance | A secure API for storing and retrieving role-play transcripts with tenant isolation and optimized querying. | Backend+Cloud |  | ✓ |  |  | ✓ |  | Azure Functions API with Cosmos DB SDK; tenant isolation via Azure AD B2C claims.
D.2.3 | Scoring & Feedback System | Transcript Storage | Add analytics indexing | • Define secondary indexes for common queries • Implement time-based partitioning • Add full-text search capabilities • Optimize for dashboard queries | Optimized Cosmos DB indexing for fast analytics queries, including full-text search and time-based partitioning. | Backend+Cloud |  | ✓ |  |  | ✓ |  | Secondary indexes on score, timestamp, and tenantId; full-text search via Azure Cognitive Search integration.
E.1.1 | Analytics & Reporting | Power BI Dashboard | Set up Power BI Embedded workspace | • Create Azure AD B2C tenant for authentication • Configure Power BI Embedded capacity in Azure • Set up Power BI workspace for multi-tenant isolation • Define RBAC roles for manager access | Power BI Embedded workspace configured with Azure AD B2C authentication and multi-tenant isolation for manager dashboards. | Backend + Cloud |  | ✓ |  |  | ✓ |  | Power BI Embedded with Azure AD B2C for authentication; capacity provisioned in Azure.
E.1.2 | Analytics & Reporting | Power BI Dashboard | Design dashboard data model | • Define schema for practice frequency, scores, and attach-rate metrics • Create relationships between user, session, and performance data • Optimize for Power BI DirectQuery to Azure Cosmos DB • Set up incremental refresh policies | Power BI data model optimized for DirectQuery to Cosmos DB, supporting incremental refresh for performance metrics. | Backend + Cloud |  | ✓ |  |  | ✓ |  | DirectQuery to Cosmos DB with incremental refresh; schema optimized for manager analytics.
E.1.3 | Analytics & Reporting | Power BI Dashboard | Build dashboard UI components | • Create React components for embedding Power BI reports • Implement tenant-specific workspace switching • Add filters for date ranges, associate IDs, and difficulty levels • Style dashboard to match white-label branding | React-based UI for embedding Power BI reports with tenant-specific workspace switching and custom filters. | Frontend + Backend | ✓ | ✓ |  |  |  |  | Power BI Embedded React components with tenant isolation; styled for white-label compliance.
E.1.4 | Analytics & Reporting | Power BI Dashboard | Implement API for dashboard data | • Create Azure Function endpoints for Power BI dataset queries • Secure endpoints with Azure AD B2C tokens • Add caching layer for frequent queries • Log API usage for audit trails | Azure Function API endpoints for Power BI dataset queries, secured with Azure AD B2C and caching for performance. | Backend + Cloud |  | ✓ |  |  | ✓ |  | Azure Functions with AD B2C security; Redis cache for query performance.
E.1.5 | Analytics & Reporting | Power BI Dashboard | Deploy and configure Power BI reports | • Publish Power BI reports to embedded workspace • Configure row-level security for tenant data • Set up scheduled refresh for reports • Test cross-tenant data isolation | Power BI reports deployed to embedded workspace with row-level security and scheduled refresh for tenant data. | Backend + Cloud |  | ✓ |  |  | ✓ |  | Row-level security enforced in Power BI; scheduled refresh from Cosmos DB.
F.1.1 | Infrastructure & DevOps | CI/CD Pipeline | Set up GitHub Actions workflows | • Create workflow for backend deployment • Create workflow for frontend deployment • Configure secrets and environment variables • Set up branch protection rules | Automated deployment pipelines for both frontend and backend, triggered on push to main branch with environment-specific configurations. | DevOps+Cloud |  |  |  | ✓ | ✓ |  | GitHub Actions with Azure credentials stored as secrets; workflows use Azure CLI for deployments.
F.1.2 | Infrastructure & DevOps | CI/CD Pipeline | Develop Bicep templates for Azure resources | • Define templates for Azure Functions and API Management • Create templates for Cosmos DB and Blob Storage • Set up templates for Azure Monitor and Log Analytics • Parameterize templates for multi-tenant environments | Infrastructure-as-code templates for provisioning all required Azure resources with tenant isolation support. | DevOps+Cloud |  |  |  | ✓ | ✓ |  | Bicep templates with modular design for reusability; parameter files for different environments.
F.1.3 | Infrastructure & DevOps | CI/CD Pipeline | Configure deployment environments | • Set up development, staging, and production environments • Configure environment-specific variables • Implement blue-green deployment strategy • Set up rollback mechanisms | Isolated environments with proper configuration management and deployment strategies to minimize downtime. | DevOps+Cloud |  |  |  | ✓ | ✓ |  | Azure Resource Groups for environment isolation; Azure Traffic Manager for blue-green deployments.
F.2.1 | Infrastructure & DevOps | Monitoring & Logging | Set up Azure Monitor for application insights | • Configure application performance monitoring • Set up custom metrics for API response times • Create alerts for error thresholds • Integrate with Azure Functions and API Management | Real-time monitoring of application performance with custom metrics and alerting for critical issues. | DevOps+Cloud |  |  |  | ✓ | ✓ |  | Azure Application Insights with custom queries for API performance metrics.
F.2.2 | Infrastructure & DevOps | Monitoring & Logging | Configure Log Analytics workspace | • Create Log Analytics workspace • Set up diagnostic settings for Azure resources • Configure log retention policies • Create custom log queries for common issues | Centralized logging solution with configurable retention and custom queries for troubleshooting. | DevOps+Cloud |  |  |  | ✓ | ✓ |  | Log Analytics workspace with 30-day retention policy; KQL queries for common troubleshooting scenarios.
F.2.3 | Infrastructure & DevOps | Monitoring & Logging | Implement alerting and notification system | • Set up email notifications for critical alerts • Configure Slack/Teams integration for team notifications • Create alert rules for performance degradation • Implement alert escalation policies | Multi-channel alerting system with configurable rules and escalation policies for critical issues. | DevOps+Cloud |  |  |  | ✓ | ✓ |  | Azure Monitor alerts with Action Groups for multi-channel notifications; Slack webhook integration.