## Effort Estimation
No | Functionality Type | Module | Feature | Task | Sub Task | Complexity | Dependencies | Frontend (hrs) | Backend (hrs) | AI/ML (hrs) | Integration (hrs) | Cloud Infrastructure (hrs) | DevOps (hrs) | Security (hrs) | Data Engineering (hrs) | QA (hrs) | Tech Remarks | BA Remarks
A.0 | Project Setup | - | Monorepo & CI/CD initialization | Environment Setup | Azure resource provisioning, GitHub Actions setup, dev/staging/prod environments | Medium-High |  | 0 | 0 | 0 | 0 | 10 | 16 | 0 | 0 | 0 | Critical path — all modules blocked until this ships. Using Azure CLI and ARM templates for infrastructure as code.
A.1 | Project Setup | - | Architecture & Tech Spike | Technology Validation | Validate Azure OpenAI and 11 Labs integration with sample prompts and voice synthesis | Medium | A.0 | 0 | 4 | 12 | 8 | 0 | 0 | 0 | 0 | 4 | Spike to confirm latency and cost assumptions. Uses Azure OpenAI GPT-4o-mini for cost control during testing.
B.0 | Authentication | Backend | Azure AD B2C Configuration | Identity Provider Setup | Configure Azure AD B2C tenant, user flows, and OAuth 2.0 settings for email/password auth | Medium | A.0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 4 | Uses custom policies for branding. Assumes standard email/password provider sufficient for MVP.
B.1 | Authentication | Backend | Token Management | API Security Implementation | Implement JWT validation middleware and role-based access control for API endpoints | Medium-High | B.0 | 0 | 16 | 0 | 0 | 0 | 0 | 8 | 0 | 6 | Uses Azure AD B2C tokens. Roles: sales_associate, manager, admin. No refresh token rotation in MVP.
B.2 | Authentication | Frontend | Login/Logout UI | Authentication Components | Build login form, password reset, and logout functionality with form validation | Medium | B.0, B.1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Uses MSAL.js for auth. Assumes Azure AD B2C handles MFA. Error states include network failure and invalid credentials.
C.0 | AI Role-play | Backend | Conversation Engine | Core API Endpoints | Implement REST API for starting conversations, sending messages, and ending sessions | Medium-High | B.1 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Stateless design with session ID. Uses HTTP POST for message exchange. Rate limiting at 30 req/min per user.
C.1 | AI Role-play | AI/ML | Prompt Engineering | Scenario Prompt Templates | Design and test prompt templates for different sales scenarios (objection handling, product pitch, closing) | High | A.1 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 6 | Uses few-shot learning with 3 examples per scenario. Focuses on ESP upsell techniques. Temperature set to 0.7 for balanced creativity.
C.2 | AI Role-play | AI/ML | Response Processing | Scoring Mechanism Implementation | Develop algorithm to score user responses based on scenario objectives and conversation flow | High | C.1 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 8 | Scoring rubric: 0-100 based on objection handling (30%), product knowledge (30%), closing technique (20%), rapport building (20%). Uses keyword matching and semantic similarity.
C.3 | AI Role-play | Backend | Conversation State Management | Session Persistence | Implement Redis-backed session store for conversation history and context | Medium | C.0 | 0 | 12 | 0 | 0 | 8 | 0 | 0 | 0 | 4 | Uses Azure Cache for Redis. Stores last 10 exchanges per session. TTL of 2 hours for inactive sessions.
D.0 | Voice Service | Integration | 11 Labs Integration | Text-to-Speech Implementation | Integrate 11 Labs API for converting AI responses to speech with voice selection and error handling | Medium | C.0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 6 | Uses 11 Labs 'Bella' voice (friendly female). Implements retry logic with exponential backoff. Caches common phrases to reduce API calls.
D.1 | Voice Service | Frontend | Audio Playback | Voice Interface Components | Build audio player controls with play/pause, volume control, and error states for voice playback | Medium | D.0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Uses HTML5 Audio API. Assumes MP3 format from 11 Labs. Includes fallback to text-only if voice service fails.
E.0 | Content Management | Cloud Infrastructure | Knowledge Base Storage | Blob Storage Setup | Configure Azure Blob Storage containers for training content (brochures, PowerPoint, sales pitches) | Low | A.0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 2 | Uses hot tier for frequently accessed content. Implements SAS tokens for secure access. Container per content type.
E.1 | Content Management | Backend | Content Retrieval | Content API Endpoints | Implement API endpoints to list, retrieve, and upload training content from Blob Storage | Medium | E.0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Supports PDF, PPTX, DOCX formats. Max file size 10MB. Uses streaming for large files to avoid memory issues.
E.2 | Content Management | Frontend | Content Upload Interface | Admin Content Management | Build UI for uploading and managing training content with drag-and-drop and file validation | Medium | E.1 | 16 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | Only accessible to admin/manager roles. Shows upload progress and success/error states. Validates file types and sizes.
F.0 | User & Session Data | Backend | Database Schema | SQL Database Design | Design and implement Azure SQL Database schema for users, sessions, transcripts, and scores | Medium | A.0 | 0 | 16 | 0 | 0 | 0 | 4 | 4 | 0 | 6 | Uses serverless tier. Tables: Users, Sessions, Messages, Scores. Indexes on user_id and session_id for query performance.
F.1 | User & Session Data | Backend | Data Access Layer | ORM Implementation | Implement data access layer with Entity Framework Core for CRUD operations on session and transcript data | Medium | F.0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Uses connection pooling. Implements retry logic for transient faults. No stored procedures in MVP for simplicity.
G.0 | Analytics & Reporting | Data Engineering | Usage Tracking | Application Insights Instrumentation | Instrument frontend and backend to track practice frequency, session duration, and score improvements | Medium | C.0, F.1 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 12 | 6 | Tracks custom events: session_start, message_sent, session_complete, score_updated. Samples at 50% to control costs.
G.1 | Analytics & Reporting | Data Engineering | Attach Rate Integration | Logic Apps Workflow | Create Azure Logic App to extract practice metrics from Application Insights and POST to internal attach rate reporting system | Medium-High | G.0 | 0 | 0 | 0 | 18 | 0 | 4 | 0 | 10 | 8 | Runs hourly. Maps practice frequency to attach rate uplift prediction. Uses HTTP endpoint with API key authentication.
G.2 | Analytics & Reporting | Frontend | Manager Dashboard | Oversight Interface | Build dashboard for managers to view team practice metrics, score trends, and transcript reviews | High | G.0, G.1 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 10 | Shows aggregate and individual metrics. Includes filters by date, user, and scenario. Transcript viewer with highlighting of key phrases.
G.3 | Analytics & Reporting | Backend | Transcript Storage | Conversation History | Implement endpoint to retrieve full conversation transcripts with timestamps and speaker labels | Medium | F.1 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Returns JSON array of messages with role (user/assistant), content, and timestamp. Limited to last 50 exchanges per session.
H.0 | User Interface | Frontend | Role-play Interface | Conversation UI Components | Build chat interface with message bubbles, typing indicators, and scenario context display | Medium | C.0, B.2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Uses virtual scrolling for long conversations. Auto-scrolls to latest message. Shows AI avatar and name (Alex).
H.1 | User Interface | Frontend | Scenario Selection | Content Library UI | Create grid view of available sales scenarios with filters by difficulty level and topic | Medium | E.2 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Shows scenario description, difficulty (1-5), and estimated time. Difficulty based on objection complexity and product knowledge required.
H.2 | User Interface | Frontend | Practice History | Personal Dashboard | Build user dashboard showing personal practice streaks, average scores, and recent sessions | Medium | G.0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Updates in real-time via SignalR. Shows progress toward daily/weekly goals. Includes badge system for milestones.
I.0 | DevOps & Deployment | - | CI/CD Pipeline | Build and Release Automation | Set up Azure DevOps pipelines for building, testing, and deploying frontend and backend to Azure | Medium-High | A.0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | Uses multi-stage pipelines. Includes security scanning (OWASP ZAP) and performance testing. Blue-green deployment for zero downtime.
I.1 | DevOps & Deployment | - | Environment Configuration | Secrets and Configuration Management | Implement secure management of API keys, connection strings, and service principals using Azure Key Vault | Medium | A.0, I.0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 0 | 4 | Frontend uses app settings with MSI. Backend uses Managed Identity. Rotates secrets every 90 days.
J.0 | Testing & QA | - | Test Strategy | Test Planning and Design | Create test plan covering unit, integration, and end-to-end scenarios for all user roles | Medium | A.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | Uses test pyramid: 70% unit, 20% integration, 10% E2E. Includes accessibility and security testing. Test data includes edge cases.
J.1 | Testing & QA | Frontend | Component Testing | Unit Test Implementation | Write and maintain unit tests for React components using Jest and React Testing Library | Medium | H.0, H.1, H.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Mocks API calls with MSW. Tests cover loading, error, and success states. Aims for 80% component coverage.
J.2 | Testing & QA | Backend | API Testing | Integration Test Suite | Develop integration tests for API endpoints using xUnit and mocking frameworks | Medium | C.0, E.1, F.1, G.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | Uses in-memory SQL Database for testing. Tests authentication, authorization, and business logic. Includes contract tests for 11 Labs and OpenAI.
J.3 | Testing & QA | - | End-to-End Testing | User Journey Validation | Implement E2E tests for complete user journeys: login -> scenario selection -> role-play -> logout | Medium-High | J.0, J.1, J.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | Uses Playwright for cross-browser testing. Tests mobile and desktop viewports. Includes voice playback simulation.
K.0 | Performance & Scaling | Backend | Load Testing | Performance Benchmarking | Conduct load testing to validate system handles 100 concurrent users during peak lull periods | Medium-High | I.0 | 0 | 12 | 8 | 6 | 4 | 8 | 0 | 0 | 10 | Uses Azure Load Testing. Simulates 5-minute sessions with 3 message exchanges. Target: <2s response time for 95th percentile.
L.0 | Documentation & Training | - | User Documentation | End-user Guides | Create quick-start guides and video tutorials for sales associates and managers | Low | J.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Available in-platform as help center. Includes screenshots and short videos (<2 min). Updated with each release.
| TOTALS | [6 empty] | 98 | 138 | 64 | 42 | 34 | 74 | 32 | 40 | 186 | Grand Total: 608.0 hrs